## Sheet1
TaskID | Task Name | Owner | Task Assigned to | Start Date | End Date | Status
1 | Understanding requirements | FlyAway | Heera P | 2022-04-20 | 2022-04-20 | Completed
2 | Design flowchart and Write Algorithm | FlyAway | Heera P | 2022-04-21 | 2022-04-21 | Completed
3 | Design classes | FlyAway | Heera P | 2022-04-22 | 2022-04-22 | Completed
4 | Develop code | FlyAway | Heera P | 2022-04-23 | 2022-05-02 | Completed
5 | Tetsing | FlyAway | Heera P | 2022-04-23 | 2022-05-02 | Completed
6 | Pushing code to GitHub | FlyAway | Heera P | 2022-05-03 | 2022-05-03 | Completed